## Defect Log
Indian Creek Cycles — Defect Log
Total Defects | 6 |  | High Severity | 1
Closed | 6 |  | Medium Severity | 4
Open | 0 |  | Low Severity | 1
Defect ID | Related Test | Module | Summary | Description | Expected Result | Actual Result | Severity | Priority | Environment | Status | Evidence | Discovery Type | Resolution Notes
BUG-001 | Exploratory | Admin Dashboard | Dashboard displays past reservations as active | The admin dashboard counted reservations whose end dates had already passed as active. | Only reservations currently occurring should be counted as active. | Past paid, completed, or pending reservations were included in the active reservation count. | Medium | Medium | Google Chrome on macOS | Closed | evidence/BUG-001-dashboard-summary.png; evidence/BUG-001-recent-reservations.png | Exploratory Testing | Active reservation logic updated to count only current confirmed, paid, or active reservations.
BUG-002 | Exploratory | Reservation Management | Expired pending reservations never transition to a final status | Reservations remained Pending after their reservation period ended. | After a configurable grace period, expired pending reservations should transition to a final status such as Cancelled. | Reservations remained Pending after the reservation end date passed. | Medium | Medium | Google Chrome on macOS — Admin Dashboard | Closed | evidence/BUG-002-pending.png | Exploratory Testing | A configurable 24-hour grace period and automatic pending-reservation expiration utility were added.
BUG-003 | Exploratory | Ride Guide / Customer Information | Ride Guide does not explain pending reservation expiration | The Ride Guide did not explain how long a reservation could remain Pending or when an unpaid reservation would be cancelled. | The Ride Guide should explain the grace period, cancellation timing, and how to request an exception. | Customers were not provided information about the pending reservation expiration policy. | Low | Medium | Google Chrome on macOS | Closed | evidence/BUG-003-ride-guide.png | Exploratory Testing | A Ride Guide FAQ was added explaining the pending reservation grace period and automatic cancellation policy.
BUG-004 | Exploratory | Dashboard / Revenue Reporting | Dashboard revenue total does not match revenue breakdown | The dashboard revenue total excluded rental add-on revenue and did not match the Revenue Breakdown page. | Dashboard revenue should equal bike rentals plus rental add-ons plus merchandise revenue. | Dashboard displayed $782.00 while the Revenue Breakdown displayed $863.00. | High | High | Google Chrome on macOS — Admin Dashboard | Closed | evidence/BUG-004-dashboard-revenue.png; evidence/BUG-004-revenue-breakdown.png | Exploratory Testing | Rental add-on revenue was added to the dashboard total and displayed as a separate category.
BUG-005 | TC-014 | Navigation / Responsive Design | Website navigation breaks at browser zoom levels above 150% | At 175% browser zoom, the navigation became unusable. | The website should remain fully functional and navigable at increased browser zoom levels. | The navigation bar disappeared, the hamburger menu stopped working, and the logo no longer returned users to the homepage. | Medium | Medium | Google Chrome on macOS — 175% zoom | Closed | evidence/BUG-005_TC_014_BrowserZoomBreaksNavigation.png | Accessibility / Responsive Testing | Responsive navigation breakpoints were adjusted so the menu remains available at intermediate widths.
BUG-006 | TC-015 | Accessibility / Keyboard Navigation | Continuous keyboard navigation requires mouse interaction | Keyboard-only users could not continuously move between the header navigation and page content. | All interactive elements should be reachable using Tab, Shift+Tab, and Enter without mouse interaction. | Keyboard navigation worked within sections, but clicking the page was required before focus navigation could continue. | Medium | Medium | Google Chrome on macOS | Closed | evidence/BUG-006_TC_015_KeyboardNavigationFocusIssue.mov | Accessibility Testing | Keyboard focus behavior and accessibility states were updated and retested.
Repository location: indian-creek-cycles-qa/bug-reports/Defect_Log.xlsx